## risk register
Risk ID | Risk Description | Cause | Probability (1-5) | Impact (1-5) | Owner | Category | Mitigation Plan | Mitigation Owner | Next Review Date | Management Actions | Status | Risk Exposure (RE) | Risk Priority
R1 | Server/Hosting Failure during peak registration | High traffic overload, poor server capacity | 4 | 5 | Iqra | Technical | Use scalable hosting & load testing | Ayyan | 2025-11-07 | Activate backup server if failure | Open | 20 | 1
R2 | Data Security Breach (student information leak) | Weak authentication, unprotected database | 3 | 5 | Unaiza | Resource | Enable encryption & secure authentication | Iqra | 2025-11-10 | Block access & reset credentials | Open | 15 | 2
R3 | Development Delay | Limited resources, team availability issues | 4 | 3 | Ayyan | Resource | Monitor tasks & allocate backup developer | Unaiza | 2025-11-14 | Adjust project scope if delayed | Monitoring | 12 | 3
R4 | Incorrect registration data from students | Missing validation, user input errors | 3 | 3 | Iqra | Schedule | Input validation & data checks | Ayyan | 2025-11-07 | Allow corrections & re-submission | Monitoring | 9 | 4
R5 | System usability issues (difficult UI) | Poor design, lack of usability testing | 2 | 3 | Unaiza | Technical | Improve UI & conduct usability testing | Iqra | 2025-11-10 | Provide proper walkthrough | Closed | 6 | 5

## dashboard
RMMM Dashboard
|  |  |  | Priority | Count |  | Category | Count
Total Risks | 5 |  |  | High | 3 |  | Technical | 2
High Priority | 3 |  |  | Medium | 1 |  | Schedule | 1
Medium Priority | 1 |  |  | Low | 1 |  | Resource | 2
Low Priority | 1
Mitigated (has Mitigation Plan) | 5
% Mitigated | 1
| Impact → | 1 | 2 | 3 | 4 | 5
1 |  | 0 | 0 | 0 | 0 | 0
2 |  | 0 | 0 | 0 | 0 | 0
3 |  | 0 | 0 | 4 | 0 | 0
4 |  | 0 | 0 | 0 | 0 | 3
5 |  | 0 | 0 | 0 | 1 | 2